## Sheet1
Week | Objectives | Key Tasks | Expected Outcomes | Details
1 | Define roles and requirements | - Conduct detailed interviews with stakeholders | Clear understanding of each role's needs | Identify specific data and insights required for MD, BUD, FL, SM, BM, SR roles.
|  | - Document and prioritize insights required for each role | Role-based insights list | Catalog necessary data points and formats preferred by each role.
|  | - Assess current data availability and identify gaps | Data inventory and gap analysis | Determine if existing data supports the required insights or if additional sources are needed.
2 | Develop role-based insight models | - Design preliminary model frameworks based on role needs | Initial models for each role | Create prototype models tailored to the specific information needs of different roles.
|  | - Begin model training with available data | Data-driven insights for each role | Use historical sales and interaction data to start model training.
|  | - Establish initial data pipelines | Streamlined data input process | Automate the process of data collection and integration for continuous training and insights.
3 | Test and refine models | - Conduct initial testing with historical data | Preliminary test results | Evaluate model performance and relevance of generated insights against historical outcomes.
|  | - Collect and analyze stakeholder feedback on model outputs | Feedback document for model refinement | Gather detailed feedback from each role on the accuracy and applicability of insights.
|  | - Refine models based on initial tests and feedback | Improved model accuracy and relevance | Adjust models to better reflect role-specific needs and to address any inaccuracies.
4 | Enhance data automation and integration | - Develop and implement data cleansing and preprocessing scripts | Clean and standardized data for modeling | Ensure data quality and consistency to improve model performance.
|  | - Validate and verify automated data pipelines | Reliable automated data workflows | Test and secure data pipelines to ensure stable and efficient data flow.
5 | Advanced model refinement | - Iterate on model training with updated datasets | More accurate and relevant models | Incorporate new data and feedback into ongoing model training to enhance performance.
|  | - Integrate additional data sources, if available | Expanded data foundation for insights | Leverage broader datasets to enrich insights and improve model robustness.
|  | - Fine-tune model parameters based on continuous feedback | Tailored insights for each role | Refine models to ensure insights are precisely aligned with each role’s specific needs.
6 | Develop and test email automation | - Design role-specific email templates for insight distribution | Customized templates for each job level | Create clear, actionable email content that conveys insights effectively for each role.
|  | - Implement automation triggers based on insight generation | Operational email automation system | Set up system triggers to send emails when new insights are generated, ensuring timely delivery.
7 | Conduct User Acceptance Testing (UAT) | - Organize UAT sessions with representatives from each role | Detailed user feedback on system usability | Collect constructive feedback on the system’s functionality, insight relevance, and email clarity.
|  | - Refine system based on UAT feedback | Refined and user-approved system | Implement changes to address any user concerns, improving the overall utility and user experience.
8 | Final preparations for rollout | - Develop comprehensive training materials for all users | Ready-to-deploy training resources | Create user guides, FAQs, and training sessions to ensure users understand how to utilize the system.
|  | - Finalize system documentation and support resources | Complete documentation for system maintenance | Provide clear documentation for system upkeep and troubleshooting to ensure sustainability.
9 | Soft launch and initial monitoring | - Initiate soft launch to a select group of users | Feedback on system performance in real scenarios | Monitor system usage, collect user feedback, and measure performance metrics during soft launch.
|  | - Continuous monitoring and data collection | Initial performance data | Track system stability, user engagement, and accuracy of insights delivered.
10 | Full system rollout and ongoing optimization | - Execute full system rollout to all users | System operational for all intended users | Ensure all sales team members have access to and are utilizing the system.
|  | - Implement ongoing optimization based on usage data | Continuously improved system efficiency and relevance | Analyze system usage and feedback to make regular updates and maintain relevance.

## Sheet2
Week | Objectives | Activities | Expected Deliverables
1 | Data Validation and Role Definition | - Review current data sets for accuracy and completeness. <br> - Define distinct roles and their data needs based on organizational hierarchy. | - Validated data sets. <br> - Detailed role definitions and associated data requirements.
2 | Model Refinement | - Incorporate feedback into model improvement. <br> - Test different data sets with the model. <br> - Begin developing role-based logic in the model. | - Updated model with initial role-based logic. <br> - Test results and adjustments log.
3 | Role-based Logic Enhancement | - Refine role-based logic for model. <br> - Conduct initial testing for role-specific outcomes. <br> - Gather initial feedback from test users. | - Enhanced model with refined role-based logic. <br> - Feedback report from initial user tests.
4 | Interface and User Experience | - Improve the user interface based on role requirements. <br> - Implement feedback mechanisms within the platform. <br> - Test the interface with a small group of users. | - Updated user interface. <br> - Integrated feedback mechanisms.
5 | Full-scale Testing | - Conduct full-scale testing across all roles. <br> - Collect comprehensive feedback on user experience and accuracy of insights. <br> - Begin addressing any technical issues. | - Comprehensive test results. <br> - List of technical improvements needed.
6 | Technical Improvements and Refinement | - Implement technical improvements. <br> - Refine insight algorithms based on feedback. <br> - Prepare documentation and training materials for different roles. | - Updated and improved model. <br> - Documentation and training materials for rollout.
7 | Training and Deployment | - Conduct training sessions for each role. <br> - Begin phased deployment of the solution to the sales team. <br> - Establish a support and feedback loop for ongoing improvement. | - Completed training sessions. <br> - Initial deployment of the solution. <br> - Established support framework.
8 | Review and Iteration | - Review feedback from the initial deployment. <br> - Make necessary adjustments to the model and user interface. <br> - Plan for the next phase of deployment or additional features. | - Feedback review report. <br> - Updated plan for continued improvement and deployment.